## گزارش اصلي
ID | Fig. No. | Item No. | Module | TUGA Substitute Part Number | Old System Part No. | Description | Units Per End Item | Assembly | Standard Part | New Manufacturing Responsible Department | Level | Disassembled | شناسنامه پیشرفت | 3D Scan پیشرفت | 3D Scan مدرك | Fi100%l Modelling | Fi100%l Modelling مدرك | Level 2 Drawing | Level 2 Drawing مدرك | Level 3 Drawing | Level 3 Drawing مدرك | Assembly Drawing | نقشه ساخت با نگرش مونتاژی | گزارش شناسايي (دفترچه متالوژيكي قطعه) | گزارش شناسايي (دفترچه متالوژيكي قطعه) مدرك | اسپك ماده خام | اسپك ماده خام مدرك | اسپک قطعه | اسپک قطعه مدرك | اسپك پوشش | اسپك پوشش مدرك | اسپك اتصالات | اسپك اتصالات مدرك | ساير اسپك‌ها (عمليات تكميلي) | ساير اسپك‌ها مدرك | نقشه هاي ميان فرآيندي | نقشه هاي ميان فرآيندي مدرك | OPC يا MPP (راتينگ) | راتينگ مدرك | TP | TP مدرك | MQCP | MQCP مدرك | ITP | ITP مدرك | عقد قرارداد | ساخت دو دستگاه | ساخت 28 دستگاه | كيفيت دو دستگاه | كيفيت 28 دستگاه
5 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | پوسته-1 | 50% | 100% | 100% | 0% | 100% | AEC_208920 | 100% | AEC_208919 | 0% | 0% | 5% | 5% | 100% | AEC_200688 | 100% | AEC_501034 | 0% | 0% | NA | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 14% | 0% | 6% | 0%
7 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | 50% | 100% | NA | 0% | 100% | AEC_208898 | 100% | AEC_208897 | 0% | 0% | 5% | 5% | 10% | AEC_502025 | 100% | AEC_502898 | 0% | 0% | NA | NA | NA | NA | NA | NA | NA | NA | 10% | AEC_503316 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 9% | 0%
8 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | 50% | 100% | NA | 0% | 100% | AEC_208900 | 100% | AEC_208899 | 0% | 0% | 5% | 5% | 10% | AEC_502025 | 100% | AEC_502898 | 0% | 0% | NA | NA | NA | NA | NA | NA | NA | NA | 10% | AEC_503317 | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 9% | 0%
10 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 5 | NO | NO | متيبيسات | سیل-2 | 50% | 100% | NA | 0% | 100% | AEC_210373 | 100% | AEC_210372 | 0% | 0% | 5% | 5% | 0% | 0% | 100% | AEC_510790 | 0% | 0% | NA | NA | NA | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 6% | 0%
12 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 2 | NO | NO | جانبی الکتریکی | سایر قطعات-3 | 100% | 100% | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | 5% | 5% | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724 | 100% | 100% | 0% | 6% | 0%

## طراحي
ID | Fig. No. | Item No. | Module | TUGA Substitute Part Number | Old System Part No. | Description | Units Per End Item | Assembly | Standard Part | New Manufacturing Responsible Department | Level | Disassembled | شناسنامه پیشرفت | 3D Scan پیشرفت | 3D Scan مدرك | Fi100%l Modelling | Fi100%l Modelling مدرك | Level 2 Drawing | Level 2 Drawing مدرك | Level 3 Drawing | Level 3 Drawing مدرك | Assembly Drawing | نقشه ساخت با نگرش مونتاژی | كد مدرك شناسنامه
5 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | پوسته-1 | 50% | 100% | 100% | 0% | 100% | AEC_208920 | 100% | AEC_208919 | 0% | 0% | 5% | 5% | AEC_205084
7 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | 50% | 100% | NA | 0% | 100% | AEC_208898 | 100% | AEC_208897 | 0% | 0% | 5% | 5% | AEC_205086
8 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | 50% | 100% | NA | 0% | 100% | AEC_208900 | 100% | AEC_208899 | 0% | 0% | 5% | 5% | AEC_205087
10 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 5 | NO | NO | متيبيسات | سیل-2 | 50% | 100% | NA | 0% | 100% | AEC_210373 | 100% | AEC_210372 | 0% | 0% | 5% | 5% | AEC_205089
12 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 2 | NO | NO | جانبی الکتریکی | سایر قطعات-3 | 100% | 100% | 100% | 0% | 100% | 0% | NA | NA | 0% | 0% | 5% | 5% | AEC_205091
[12 empty] | 0% | 100% | 8% | 0% | 1% | 0% | SubContract | 0% | 0% | 0% | 5% | 5% | AEC_205092
[12 empty] | 0% | 100% | 8% | 0% | 1% | 0% | SubContract | 0% | 0% | 0% | 5% | 5% | AEC_205094
[12 empty] | 100% | 100% | 8% | 0% | 1% | 0% | SubContract | 0% | 0% | 0% | 5% | 5% | AEC_205095
[12 empty] | 100% | 100% | 100% | 0% | 100% | AEC_220709 | 100% | AEC_220412 | 0% | 0% | 5% | 5% | AEC_205098
[12 empty] | 100% | 100% | 100% | 0% | 100% | 0% | NA | NA | 0% | 0% | 5% | 5% | AEC_205099
[12 empty] | 100% | 100% | 100% | 0% | 100% | 0% | NA | NA | 0% | 0% | 5% | 5% | AEC_205101
[12 empty] | 100% | 100% | 100% | 0% | 100% | 0% | NA | NA | 0% | 0% | 5% | 5% | AEC_205102
[12 empty] | 100% | 100% | 100% | 0% | 100% | 0% | NA | NA | 0% | 0% | 5% | 5% | AEC_205103
[12 empty] | 100% | 100% | NA | 0% | 100% | AEC_502718 | 100% | AEC_502294 | 0% | 0% | 5% | 5% | AEC_205104

## جانبي
ID | Fig. No. | Item No. | Module | TUGA Substitute Part Number | Old System Part No. | Description | Units Per End Item | Assembly | Standard Part | New Manufacturing Responsible Department | Level | Disassembled | شناسنامه پیشرفت | 3D Scan پیشرفت | 3D Scan مدرك | Fi100%l Modelling | Fi100%l Modelling مدرك | Level 2 Drawing | Level 2 Drawing مدرك | Level 3 Drawing | Level 3 Drawing مدرك | Assembly Drawing | نقشه ساخت با نگرش مونتاژی | گزارش شناسايي (دفترچه متالوژيكي قطعه) | گزارش شناسايي (دفترچه متالوژيكي قطعه) مدرك | اسپك ماده خام | اسپك ماده خام مدرك | اسپک قطعه | اسپک قطعه مدرك | اسپك پوشش | اسپك پوشش مدرك | اسپك اتصالات | اسپك اتصالات مدرك | ساير اسپك‌ها (عمليات تكميلي) | ساير اسپك‌ها مدرك | نقشه هاي ميان فرآيندي | نقشه هاي ميان فرآيندي مدرك | OPC يا MPP (راتينگ) | راتينگ مدرك | TP | TP مدرك | MQCP | MQCP مدرك | ITP | ITP مدرك
5 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | پوسته-1 |  |  | 100% | 0% | 100% | 0% | NA | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
7 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 |  |  | 100% | 0% | 100% | 0% | NA | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
8 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 |  |  | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
10 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 5 | NO | NO | متيبيسات | سیل-2 |  |  | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
12 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 2 | NO | NO | جانبی الکتریکی | سایر قطعات-3 |  |  | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
[14 empty] | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
[14 empty] | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
[14 empty] | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
[14 empty] | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
[14 empty] | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
[14 empty] | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
[14 empty] | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
[14 empty] | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724
[14 empty] | 100% | 0% | 100% | 0% | 100% | NA | 0% | 0% | NA | NA | 100% | AEC_221806 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100% | AEC_209725 | NA | NA | 100% | AEC_209724

## ساخت
ID | Fig. No. | Item No. | Module | TUGA Substitute Part Number | Old System Part No. | Description | Units Per End Item | Assembly | Standard Part | New Manufacturing Responsible Department | Level | گزارش شناسايي (دفترچه متالوژيكي قطعه) | گزارش شناسايي (دفترچه متالوژيكي قطعه) مدرك | اسپك ماده خام | اسپك ماده خام مدرك | اسپک قطعه | اسپک قطعه مدرك | اسپك پوشش | اسپك پوشش مدرك | اسپك اتصالات | اسپك اتصالات مدرك | ساير اسپك‌ها (عمليات تكميلي) | ساير اسپك‌ها مدرك | نقشه هاي ميان فرآيندي | نقشه هاي ميان فرآيندي مدرك | OPC يا MPP (راتينگ) | راتينگ مدرك | TP | TP مدرك | MQCP | MQCP مدرك | ITP | ITP مدرك
5 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | پوسته-1 | 100% | AEC_200688 | 100% | AEC_501034 | 0% | 0% | NA | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | 10% | AEC_502025 | 100% | AEC_502898 | 0% | 0% | NA | NA | NA | NA | NA | NA | NA | NA | 10% | AEC_503316 | 0% | 0% | 0% | 0% | 0% | 0%
8 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | 10% | AEC_502025 | 100% | AEC_502898 | 0% | 0% | NA | NA | NA | NA | NA | NA | NA | NA | 10% | AEC_503317 | 0% | 0% | 0% | 0% | 0% | 0%
10 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 5 | NO | NO | متيبيسات | سیل-2 | 0% | 0% | 100% | AEC_510790 | 0% | 0% | NA | NA | NA | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
12 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 2 | NO | NO | جانبی الکتریکی | سایر قطعات-3 | 0% | 0% | 100% | AEC_503496 | 0% | 0% | NA | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 100% | AEC_503496 | 0% | 0% | NA | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 10% | AEC_510932 | 0% | 0% | NA | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | NA | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | AEC_510634
[12 empty] | 100% | AEC_503245 | 100% | AEC_502815 | 100% | AEC_209403 | NA | NA | NA | NA | NA | NA | NA | NA | 0% | 0% | 100% | AEC_502211 | 0% | 0% | 100% | AEC_501736
[12 empty] | 100% | AEC_503245 | 100% | AEC_502815 | 100% | AEC_209403 | NA | NA | NA | NA | NA | NA | NA | NA | 0% | 0% | 100% | AEC_502211 | 0% | 0% | 100% | AEC_501736
[12 empty] | 100% | AEC_503245 | 100% | AEC_502815 | 100% | AEC_209403 | NA | NA | NA | NA | NA | NA | NA | NA | 0% | 0% | 100% | AEC_502211 | 0% | 0% | 100% | AEC_501736
[12 empty] | 0% | 0% | 100% | AEC_503496 | 0% | 0% | NA | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 100% | AEC_503496 | 0% | 0% | NA | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 100% | AEC_503496 | 0% | 0% | NA | NA | NA | NA | NA | NA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## جانبي دو دستگاه
ID | Fig. No. | Item No. | Module | TUGA Substitute Part Number | Old System Part No. | Description | Units Per End Item | Assembly | Standard Part | New Manufacturing Responsible Department | Level | 3885 | Contract | Adv. Payment | Material Supply | Mold/Die/Fixture | Casting | Forge | Forming | Machining | Brazing/Welding | Coating | Dummy sample | First Articles | First Articles Test | Total Progress
5 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | پوسته-1 | 100% | 100% | 100% | [11 empty] | 100%
7 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | 100% | 100% | 100% | [11 empty] | 100%
8 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | 100% | 100% | 100% | [11 empty] | 100%
10 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 5 | NO | NO | متيبيسات | سیل-2 | 100% | 100% | 100% | [11 empty] | 100%
12 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 2 | NO | NO | جانبی الکتریکی | سایر قطعات-3 | 100% | 100% | 100% | [11 empty] | 100%
[12 empty] | 100% | 100% | 100% | [11 empty] | 100%
[12 empty] | 100% | 100% | 100% | [11 empty] | 100%
[12 empty] | 100% | 100% | 100% | [11 empty] | 100%
[12 empty] | 100% | 100% | 100% | [11 empty] | 100%
[12 empty] | 100% | 100% | 100% | [11 empty] | 100%
[12 empty] | 100% | 100% | 100% | [11 empty] | 100%
[12 empty] | 100% | 100% | 100% | [11 empty] | 100%
[12 empty] | 100% | 100% | 100% | [11 empty] | 100%
[12 empty] | 100% | 100% | 100% | [11 empty] | 100%

## جانبي 28 دستگاه
ID | Fig. No. | Item No. | Module | TUGA Substitute Part Number | Old System Part No. | Description | Units Per End Item | Assembly | Standard Part | New Manufacturing Responsible Department | Level | 3885 | Contract | Adv. Payment | Material Supply | Mold/Die/Fixture | Casting | Forge | Forming | Machining | Brazing/Welding | Coating | Mass Production | Total Progress
5 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | پوسته-1 | [12 empty] | 0%
7 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | [12 empty] | 0%
8 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | [12 empty] | 0%
10 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 5 | NO | NO | متيبيسات | سیل-2 | [12 empty] | 0%
12 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 2 | NO | NO | جانبی الکتریکی | سایر قطعات-3 | [12 empty] | 0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## ساخت دو دستگاه
ID | Fig. No. | Item No. | Module | TUGA Substitute Part Number | Old System Part No. | Description | Units Per End Item | Assembly | Standard Part | New Manufacturing Responsible Department | Level | 3885 | Contract | Adv. Payment | Material Supply | Mold/Die/Fixture | Casting | Forge | Forming | Machining | Brazing/Welding | Coating | Dummy sample | First Articles | First Articles Test | Total Progress
5 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | پوسته-1 |  | 100% | [12 empty] | 14%
7 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 |  | 100% | [12 empty] | 0%
8 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 |  | 100% | [12 empty] | 0%
10 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 5 | NO | NO | متيبيسات | سیل-2 |  | 100% | [12 empty] | 0%
12 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 2 | NO | NO | جانبی الکتریکی | سایر قطعات-3 |  | 100% | [12 empty] | 0%
[13 empty] | 100% | [12 empty] | 0%
[13 empty] | 100% | [12 empty] | 0%
[13 empty] | 0% | [12 empty] | 0%
[13 empty] | 100% | [12 empty] | 29%
[13 empty] | 100% | [12 empty] | 29%
[13 empty] | 100% | [12 empty] | 29%
[13 empty] | 100% | [12 empty] | 0%
[13 empty] | 100% | [12 empty] | 0%
[13 empty] | 100% | [12 empty] | 0%

## ساخت 28 دستگاه
ID | Fig. No. | Item No. | Module | TUGA Substitute Part Number | Old System Part No. | Description | Units Per End Item | Assembly | Standard Part | New Manufacturing Responsible Department | Level | 3885 | Contract | Adv. Payment | Material Supply | Mold/Die/Fixture | Casting | Forge | Forming | Machining | Brazing/Welding | Coating | Mass Production | Total Progress
5 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | پوسته-1 | [12 empty] | 0%
7 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | [12 empty] | 0%
8 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | [12 empty] | 0%
10 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 5 | NO | NO | متيبيسات | سیل-2 | [12 empty] | 0%
12 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 2 | NO | NO | جانبی الکتریکی | سایر قطعات-3 | [12 empty] | 0%
0%
0%
0%
45%
45%
45%
0%
0%
0%

## كيفيت دو دستگاه
ID | Fig. No. | Item No. | Module | TUGA Substitute Part Number | Old System Part No. | Description | Units Per End Item | Assembly | Standard Part | New Manufacturing Responsible Department | Level | بررسی و تائید ITP (4%) | ارزيابي كيفي پيمانكار (2%) | Kick Off Meeting (3%) | CDR (5%) | بازرسي كيفي مطابق ITP/MQCP (65%) | ارائه گزارش بازرسي Accept/NCR (7%) | بررسي پاسخ طراحي به NCR (5%) | صدور تگ كيفي (2%) | تدوين و تاييد Final Book (5%) | صدور Test Certificate /Form1/CoC (2%) | میزان درصد پیشرفت
5 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | پوسته-1 | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6%
7 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9%
8 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9%
10 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 5 | NO | NO | متيبيسات | سیل-2 | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6%
12 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 2 | NO | NO | جانبی الکتریکی | سایر قطعات-3 | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6%
[12 empty] | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6%
[12 empty] | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6%
[12 empty] | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6%
[12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6%
[12 empty] | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6%
[12 empty] | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6%
[12 empty] | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6%
[12 empty] | 28.5% | 28.5% | 28.5% | 28.5% | 28.5% | 28.5% | 28.5% | 28.5% | 28.5% | 28.5% | 28.5%

## كيفيت 28 دستگاه
ID | Fig. No. | Item No. | Module | TUGA Substitute Part Number | Old System Part No. | Description | Units Per End Item | Assembly | Standard Part | New Manufacturing Responsible Department | Level | بازرسي كيفي مطابق ITP/MQCP (75%) | ارائه گزارش بازرسي Accept/NCR (12%) | بررسي پاسخ طراحي به NCR (3%) | صدور تگ كيفي (2%) | تدوين و تاييد Final Book (6%) | صدور Test Certificate /Form1/CoC (2%) | درصد پیشرفت
5 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | پوسته-1 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
7 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
8 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 1 | NO | NO | متيبيسات | سایر قطعات-3 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
10 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 5 | NO | NO | متيبيسات | سیل-2 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
12 | 124B | 32B | MBC | 7125H12L32 | 32652A015-00 | FDFD JHGDV SDGHFH SFSGHDH HDHDF | 2 | NO | NO | جانبی الکتریکی | سایر قطعات-3 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[12 empty] | 22.5% | 22.5% | 22.5% | 22.5% | 22.5% | 22.5% | 22.5%